## Ideas
Idea | Implementation
Special NPC stories | prototyped | PLEASE MAKE 1 LEVEL FIRST, DO THE HIGHSCHOOL GIRL FIRST ENCOUNTER
Puzzles/ fixing phase | On hold
regular/faceless NPC dialogue template | On hold
"diagnosis" phase | In progress | Dialogues + choice part of the game, MAIN PRIORITY.
Intro scene animation | On hold | idk tho
Results menu after finishing a day | On hold
Tutorials and glossary | On hold | Initial tutorials that happens everytime you encounter a certain mechanic for the first time + a menu containing previous tutorials and certain things brought up in the game (similar to open world gacha game guide thingie)
Multiple npc/ minigames per day? | On hold | days where special npc shows up are still locked into that one ofc

## Assets (visual)
Asset | Priority | Status |  | "price" (IDR)
Main character character sheet | Medium | Prototyped |  | 200
Side character sheet | Medium | WIP |  | 400
dialogue box | Low | Done |  | 20
mc portraits | Medium | Done |  | 50
highschool girl portraits | Medium | Done
Salaryman portrait | Medium | WIP
Kid portrait | Medium | Not started
Other highschooler portrait | Low | Not started
PC UI | High | WIP | 16:9 ratio
Laptop UI | High | Not started | 16:9 ratio
phone UI | Medium | Not started
random npc portrait | Medium | Not started | generic npc, like literally just a stickman with no expression (not rlly necessary)
Menu background | Low | WIP | 640x360, Storefront background, 1 animation where the door opens when player press start/new game
Menu buttons | Low | Prototyped | just buttons
Logo | Low | Prototyped | pcb inspired
Desktop Icon | Low | Not started | the little icon on the .exe
Level select and score menu bg | Medium | WIP | 640x360, using the same bg for both, animated, needs animation for winning, losing, and pressing start
Results/score indicators | Low | WIP | probably just UI color adjustment and backgrounf MC animations
Gameplay background | Medium |  | MC pov from counter facing towards the door

## Implementation
Function | Priority | Status
Dialogue system | High | Canceled | Using dialogic as of now but there are some issues that makes me consider just making my own dialogue system
- Making the character's face change expressions in dialogue | High | Not started
"Desktop" click controls | Medium | Not started | make a 2 pointer system where; when when it's inside of the screen use a pointer like texture and when a real life dialogue pops up, change it into a hand like pointer
First puzzle | High | Not started
Scoring system (money) | Medium | Not started
Main Menu | Low | WIP
Settings | Low | Not started
save system | Medium |  | not a full blown save like rpgs but more like the original PvZ where you keep track of the score and progress which you can continue from

## Sounds
Sounds | Priority | Status
Menu Sfx | Low | Not started
Character Dialogue noise | Medium | Not started
Menu Music | Medium | Not started | ALL THESE ARE FREE ASSETS MOST LIKELY
Dialogue/puzzle music | Medium | Not started
| Low | Not started
| Low | Not started

## Story
Story/Dialogue | Priority | Status
Week-1 Highschool girl | High | Prototyped
Week-1 Boy | High | Prototyped
Week-2 Salaryman | High | WIP
Week-2 Highschool girl(s) | Medium | Prototyped
Week-2 Boy | Medium | Prototyped
Implementations | Priority | Status